## Catalog
Project: GPC
Technical Design
0 | Preparation
1 | User Case Diagram
2 | Class Diagram
3 | Sequence Diagram
3.1 | User Register
3.2 | User Login
Project Management
1 | Task Sheet
2 | Road Map & Schedule

## Preparation
Preparation
[Dev]Environment
Module | Solution | Library
Server | NodeJS | Express.js
Database | MongoDB | MongoJS
Client | JS | AngularJS
| CSS | Bootstrap

## UserCase
User Case Diagram
Client Judge

## ClassDiagram
Class Diagram

## Sequence
Login Sequence Diagram
Register Sequence Diagram

## TaskSheet
Project | GPC
Module | Task Group | Sub Task | Description | Note | Assigner | Executor | Start Time | Due Date | Status
Environment | Dev Environment | set up developing environment | set up nodejs + mongodb developing environment |  |  | Michael.Lee | 2013-01-15 | 2013-01-16 | Finished
|  | [Demo] nodejs Server work |  |  |  | Michael.Lee | 2013-01-16 | 2013-01-16 | Finished
|  | [Demo] mongoodb work |  |  |  | Michael.Lee | 2013-01-16 | 2013-01-16 | Finished
| Porject Docs | init project design and management documents |  |  |  | Michael.Lee | 2013-01-15 | 2013-01-15 | Finished
Design | Server Framework | Server framework design documents [Class Diagram v0.1] |  |  |  | Michael.Lee | 2013-01-15 | 2013-01-15 | Finished
|  | User Login Sequence [3.1 Sequence Diagram v0.2] |  |  |  | Michael.Lee | 2013-01-16 | 2013-01-21 | Finished
|  | User Register Sequence [3.2 Sequence Diagram v0.2] |  |  |  | Michael.Lee | 2013-01-16 | 2013-01-21 | Finished
|  | User Vote Sequence [3.3 Sequence Diagram v0.1] |  |  |  | Michael.Lee | 2013-01-21 | 2013-01-22 | Finished
|  | Update Class Diagram v0.3 for vote |  |  |  | Michael.Lee | 2013-01-21 | 2013-01-21 | Finished
| Client Framework | User Case Analysis -- Client Judge |  |  |  | Michael.Lee | 2013-01-15 | 2013-01-16 | Finished
|  | Client Judge Spec Design |  |  |  | Michael.Lee | 2013-01-16 | 2013-01-21 | Finished
Dev | Client Judge | Login UI |  |  |  | Michael.Lee | 2013-01-16 | 2013-01-16 | Finished
|  | Register UI |  |  |  | Michael.Lee | 2013-01-16 | 2013-01-16 | Finished
|  | Check Register input |  |  |  | Michael.Lee | 2013-01-16 | 2013-01-16 | Finished
|  | Change Login UI Design According to Zhihu |  |  |  | Michael.Lee | 2013-01-21 | 2013-01-21 | Finished
|  | Change Register UI Design According to Zhihu |  |  |  | Michael.Lee | 2013-01-21 | 2013-01-21 | Finished
| Server Director | Director Module Core |  |  |  | Michael.Lee | 2013-01-24 | 2013-01-25 | Finished
|  | Status & StatusKeeper Link |  |  |  | Michael.Lee | 2013-01-24 | 2013-01-25 | Finished
|  | Long Polling |  |  |  | Michael.Lee | 2013-01-25 | 2013-01-25 | Finished
|  | Status Notify |  |  |  | Michael.Lee | 2013-01-24 | 2013-01-25 | Finished
|  | Start Vote |  |  |  | Michael.Lee | 2013-01-25 | 2013-01-25 | Finished
|  | End Vote |  |  |  | Michael.Lee | 2013-01-25 | 2013-01-25 | Finished
| Client Vote | Client Vote UI Design |  |  |  | Michael.Lee | 2013-01-28 | 2013-01-28 | Finished
|  | Client Long Polling -- Connection |  |  |  | Michael.Lee | 2013-01-28 | 2013-01-28 | Finished
|  | Start Vote Event |  |  |  | Michael.Lee | 2013-01-28 | 2013-01-28 | Finished
|  | End Vote Event |  |  |  | Michael.Lee | 2013-01-28 | 2013-01-28 | Finished
| Refacor | Server Director Module -- register project to project manager |  |  |  | Michael.Lee | 2013-01-29 | 2013-01-29 | Process
|  | Server Director Module -- router |  |  |  | Michael.Lee | 2013-01-29 | 2013-01-29 | Process

## RoadMap
2013
| 2013-01-15 | 2013-01-16 | 2013-01-17 | 2013-01-18 | 2013-01-19 | 2013-01-20 | 2013-01-21 | 2013-01-22 | 2013-01-23 | 2013-01-24 | 2013-01-25 | 2013-01-26 | 2013-01-27 | 2013-01-28 | 2013-01-29 | 2013-01-30 | 2013-01-31 | 2013-02-01 | 2013-02-02 | 2013-02-03 | 2013-02-04 | 2013-02-05 | 2013-02-06 | 2013-02-07 | 2013-02-08 | 2013-02-09 | 2013-02-10 | 2013-02-11
| Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon
Design & Preparation | bar: 2013-01-15 to 2013-01-17
User Center Module | bar: 2013-01-21 to 2013-01-23
Marker & DecissionMaker | bar: 2013-01-24 to 2013-01-25; 2013-01-28
Director Module | bar: 2013-01-29 to 2013-01-31
Status Manager | bar: 2013-02-01; 2013-02-04 to 2013-02-07
release
version 1 [2013-1-28] | 2013-01-15: 1.use mobile/tablet/pc to vote
2.marker collects data and calculate
3. show the result
version 2 [2013-2-7] | 2013-01-15: simply achive the all functions without full testing
1
2